## Sheet1
2156 Gantt Chart
|  | September 7-11 | September 14-18 | September 21-25 | September 27-Nov 1 | October 5-9 | October 12-16 | October 19-23 | October 26-30 | November 1-4 | November 7-11 | November 14-18 | November 18-25 | Nov 25-Dec 2 | Dec 2-9 | Dec 9-16
Phase 1 | % Completion
Create Portfolio | 100% |  | *
Phase 2: Strategy
Strategies | 100%
Drawings | 100%
FRDPARRC Tables | 100%
Update Portfolio | 100%
Phase 3: Conceptual Design
Problem Statement / Decision Matrix | 100%
Concept Decisions | 100%
FRDPARRC Tables | 100%
Portfolio Updated | 100%
Phase 4: Modules
Problem Statement / Decision Matrix | 100%
Concept Decisions | 100%
FRDPARRC Tables | 100%
Portfolio Updated | 100%
Phase 5: Components
Problem Statement / Decision Matrix | 100%
Concept Decisions | 100%
FRDPARRC Tables | 100%
Portfolio Updated | 100%
Phase 6: Drawings
Problem Statement / Decision Matrix | 100%
Solutions | 100%
Bill of Materials / Poster | 100%
Portfolio Updated | 100%
Aaron Macri