# Louise’s (Prospective) Timeline: Working with Alzheimer’s Association – Western Carolina Chapter

# Plan Year 1

5 pilot sessions between January 2006 and August 2006.

Evaluation of each session.

# Outline of tasks – Year 1

- Integrate materials into professional CEU training with Alzheimer’s Association existing materials.

Trainings scheduled:

    - Communication – Jan 13th 2006

    - Behavior – Jan 20th – 2006

Trainings will be for approximately 25 staff already working with persons with dementia in various community and facility settings – mainly CNAs. Predominantly English first language but also some ESL. Trainings are held at the Senior Center on Shamrock and are a three-hour duration. Training will be power point based. Trainings are certified for 3 CEU hours by NC Division of Family Services (i.e. applicable for CNAs – not certified for nursing CEUs).

- Approach day care (predominantly African American) and family support group (predominantly Caucasian) re: offering 1.5 hour duration training for family members in March/April. Adapt materials to shorter combined communication/behavior informal training. Training will be interactive/lecture/role-play/Q&A with some handouts etc. Only visual aid may be transparencies and paper based exercises.

- Approach additional nursing home and offer a CEU ( through DFS only) Communication/behavior training for staff and aim to offer in May 2006. Aim to get more feedback from RNs and LPNs for this pilot.

- Evaluate each program and refine content/format etc.

- Plan Year 2

  - Training/introduction of module chapter wide, work with daycares and Project CARE for further sessions, incorporate materials into the behavior training modules.

  - Integration with Project CARE will also allow for a pilot in a rural setting, urban setting, and with urban African American caregivers.

  - In-service for Chapter wide program staff.

  - One CEU module offered at each Chapter office (4 total).

  - 4 community education programs.

  - Work with National as to format – power point/video/DVD/ paper/short versions for support groups etc.

- Plan Year 3

  - Repeat, refine and package.

  - Package materials as additions to existing trainings and as a stand alone module.

  - Work with National as to format – power point/video/DVD/ paper/short versions for support groups etc.

Note: The plans for Years 2 and 3 will be more detailed later, of course, particularly as we develop the package in multiple formats