## Manual Chart
Gantt Chart Design Lab 1
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | [5 empty] | WEEK 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
[7 empty] | S | M | T | W | Th | F | S | M | T | W | Th | M | T | W | Th | F | M | T | W | T | F
Assignment 2
| Brainstorm | 2020-10-05 | 2020-10-06 | 2 | Brian | 100% | bar: WEEK 1 S to WEEK 1 M; WEEK 2 S to WEEK 2 Th; Week 4 M to Week 4 F
| Narrow Ideas | 2020-10-06 | 2020-10-06 | 1 | Brian | 100% | bar: WEEK 1 M; WEEK 2 S to WEEK 2 Th; Week 4 M to Week 4 F
| Strategies | 2020-10-06 | 2020-10-06 | 1 | Brian | 100% | bar: WEEK 1 M; WEEK 2 Th; Week 4 M to Week 4 F
| FRDPARRC Chart | 2020-10-06 | 2020-10-06 | 1 | Brian | 100% | bar: WEEK 1 M; WEEK 2 S; Week 4 M to Week 4 F
| Advising | 2020-10-07 | 2020-10-07 | 1 | Brian | 100% | bar: WEEK 1 T; WEEK 2 S; Week 4 M to Week 4 F
| Update Website | 2020-10-07 | 2020-10-07 | 1 | Brian | 100% | bar: WEEK 1 T; WEEK 2 S; Week 4 M to Week 4 F
| Submission | 2020-10-08 | 2020-10-08 | 1 | Brian | 100% | bar: WEEK 1 W; WEEK 2 S to WEEK 2 Th; Week 4 M to Week 4 F
Assignment 3 | bar: WEEK 1 S to WEEK 2 Th; Week 3 F to Week 4 T
| Update Problem Statement | 2020-10-19 | 2020-10-19 | 1 | Brian | 100% | bar: WEEK 2 S to WEEK 2 Th
| Complete Decision Matrix | 2020-10-19 | 2020-10-19 | 1 | Brian | 100% | bar: WEEK 2 S to WEEK 2 Th
| Brainstormed Concepts | 2020-10-19 | 2020-10-20 | 2 | Brian | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 2 Th
| Developed FRDARRC Tables | 2020-10-20 | 2020-10-21 | 2 | Brian | 100% | bar: WEEK 2 S; WEEK 2 T to WEEK 2 W
| Lessons Learned | 2020-10-21 | 2020-10-21 | 1 | Brian | 100% | bar: WEEK 2 S; WEEK 2 W
| Advisee Comments | 2020-10-21 | 2020-10-21 | 1 | Brian | 100% | bar: WEEK 2 S; WEEK 2 W
| Submission | 2020-10-21 | 2020-10-21 | 1 | Brian | 100% | bar: WEEK 2 S to WEEK 2 Th
Assignment 3 | bar: WEEK 1 S to Week 3 F
| Update Problem Statement | 2020-11-09 | 2020-11-09 | 1 | Brian | 100% | bar: Week 3 M
| Complete Decision Matrix | 2020-11-10 | 2020-11-10 | 1 | Brian | 100% | bar: Week 3 T
| Brainstormed Modules | 2020-11-10 | 2020-11-10 | 1 |  | 100% | bar: Week 3 T
| Sketches and CAD | 2020-11-10 | 2020-11-11 | 2 | Brian | 100% | bar: Week 3 T to Week 3 W
| Developed FRDARRC Tables | 2020-11-11 | 2020-11-11 | 1 | Brian | 100% | bar: Week 3 W
| Updated Gantt Chart | 2020-11-12 | 2020-11-12 | 1 |  | 100% | bar: Week 3 Th
| Lessons Learned | 2020-11-12 | 2020-11-12 | 1 | Brian | 100% | bar: Week 3 Th
| Advisee Comments | 2020-11-12 | 2020-11-12 | 1 | Brian | 100% | bar: Week 3 Th
| Submission | 2020-11-12 | 2020-11-12 | 1 | Brian | 100% | bar: Week 3 Th
Assignment 4
| Update Problem Statement | 2020-11-30 | 2020-11-30 | 1 | Brian | 100% | bar: Week 4 M
| Complete Decision Matrix | 2020-11-30 | 2020-11-30 | 1 | Brian | 100% | bar: Week 4 M
| Brainstormed Components | 2020-11-30 | 2020-11-30 | 1 |  | 100% | bar: Week 4 M
| Developed FRDARRC Tables | 2020-12-01 | 2020-12-01 | 1 | Brian | 100% | bar: Week 4 T
| Stress Analysis | 2020-12-02 | 2020-12-02 | 1 | bar: Week 4 W
| Sketches and CAD | 2020-12-02 | 2020-12-02 | 1 | Brian | 100% | bar: Week 4 W
| Updated Gantt Chart | 2020-12-03 | 2020-12-03 | 1 |  | 100% | bar: Week 4 T
| Lessons Learned | 2020-12-03 | 2020-12-03 | 1 | Brian | 100% | bar: Week 4 T
| Advisee Comments | 2020-12-03 | 2020-12-03 | 1 | Brian | 100% | bar: Week 4 T
| Submission | 2020-12-03 | 2020-12-03 | 1 | Brian | 100% | bar: Week 4 T
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])